## Cover Page
PART B: ELECTRICAL INSTALLATION BOQ

## Sch. 000
ELECTRICAL INSTALLATION
Schedule No. 0000 : Preambles to Bill of Quantities
Item | Description | Unit | Qty | Rate | Amount | CLAIM 3 OCTOBER | CLAIM 4+5 DECEMBER | CLAIM 5 JAN/FEB | Claim 6 - March | Claim 7 - April | MAY - CLAIM 8 | JUNE - CLAIM 9 | JULY - CLAIM 10 | AUGUST CLAIM 11 | TOTAL CLAIMED
A | PREAMBLES TO BILLS OF QUANTITIES
A.1 | These Bills of Quantities contain pages numbered consecutively.
A2 | Before the Tenderer submits his quote he should check the number of pages, and if any are found missing or duplicated, or the figures or writing indistinct, he should apply to the Engineer at once and have same rectified as no liability whatsoever will be admitted by the Engineer in respect of errors in tender due to the foregoing.
A3 | The Bills of Quantities form part of and must be read in conjunction with the Specification, which document contains the full description of the work to be done and material and equipment to be used and unless otherwise described in the Bills of Quantities, reference should be made to the Specification for the full meaning of descriptions of work to be done and materials and equipment to be used in this service.
A4 | All item rates and extensions must be priced in detail before submission of quotations
A5 | The total quoted price in the bill shall constitute the contract price of the successful Tenderer.
A6 | Contractors are advised to check their item extensions and total additions, as no claim for arithmetical errors will be considered.
A7 | No alteration, erasure or addition is to be made in the text of the Bills of Quantities. Should any alteration, erasure or addition be made, it will not be recognised but the original wording of the Bills of Quantities will be adhered to.
A8 | The priced Bills of Quantities of the successful contractor will be checked and the Engineer reserves the right to call for adjustments to any individual price and to rectify any discrepancy whilst the Total Quoted Price, as submitted, remains unaltered.
A9 | The responsibility for the accuracy of the quantities written into the Bills remains with the person who prepared the Bills. The Tenderer shall be relieved of responsibility of measuring quantities at the tender stage, and the tender sum submitted shall be in respect of the quantities set out in the Bills, although he will be required to make his assessment of items such as brackets, fixings, etc., from details stated in the Bills and shall include in the item price for such small installation materials as are required for the complete installation in accordance with the Specification.
SCH. 000_SUB-TOTAL PAGE 1 : CARRIED FORWARD TO SCHEDULE 000 SUMMARY PAGE
A10 | The quantities in these Bills of Quantities are provisional and are not to be used for ordering materials.
A11 | Variations in the scope and extent of the work included in the Bills shall be allowed to meet the Employer's requirements and shall be measured and costed at rates entered in the Bills, where appropriate, and shall form an addition to or deduction from the total of the Bills. Any items or variation for which rates have not been included in the Bills shall be agreed and priced as non-scheduled items in accordance with the provisions of the contract.
A12 | Unless a separate rate for the supply and for the installation of any items is specifically called or, the supply and installation costs of any item shall be fully included in the unit price.
A13 | The description of each item shall, unless otherwise stated herein, be held to include making, conveying and delivery, unloading storing, unpacking, hoisting, setting, fitting and fixing in position, cutting and waste, patterns, models and templates, plant, temporary works, return of packings, establishment charges, profit and all other obligations arising out of the Conditions of Contract.
A14 | All measurements are nett, unless otherwise stated, and Tenderers must allow in the rate for wastage.
A15 | Hangars, supports, splices, joining drilling etc shall form part of unit rate.
A16 | All materials or equipment specified under a trade name, catalogue or reference number shall, for competitive tender pricing, be exactly as described in this tender.
SCH. 000_SUB-TOTAL PAGE 2 : CARRIED FORWARD TO SCHEDULE 000 SUMMARY PAGE
B | PREAMBLES
B1 | CABLE DUCT
Description of Cable duct shall be deemed to include
cable duct joints, fittings, supports, brackets, painting,
etc
B2 | OL 9000 WIRING CHANNEL
Descriptions of wiring chanel shall be deemed to include
joints or screwed connections to chanel,brackets
painting, supports, etc.
B3 | Assembling
Descriptions of manufactured items shall be
deemed to include for complete assembling and
handing over in a proper working order.
B4 | Pricing
It is expected from the Tenderer to price each
individual item in this bill of quantities and no
alterations, omissions or additions shall be made
to the bill or specification.
B5 | Value Added Tax (VAT)
Prices for individual items in this bill must be
exclusive of VAT. Provision has been made
in the Final Summary of this bill for the lump sum
addition of VAT.
SCH. 000_SUB-TOTAL PAGE 3 : CARRIED FORWARD TO SCHEDULE 000 SUMMARY PAGE
D | GENERAL
D1 | Commissioning & Testing
| Allowance for the inspection, commissioning and applicable testing of the entire installation as described. (Including certificates) | Item | 1 | 34650 | 34650
0
D2 | Preliminaries |  |  |  | 0
0
D2.1 | Engineering, contract administration and contract management | Item | 1 | 792000 | 792000 | 20001.96 | 20001.96 | 60000 | 20000 | 35000 | 25000 | 20000 |  |  | 200003.92
0
D2.2 | Liaison and co-ordination with other services | Item | 1 | 4950 | 4950
0
D3 | Guarantee |  |  |  | 0
0
D3.1 | Allowance for 12 month guarantee as described | Item | 1 | 49500 | 49500
0
D4 | Maintenance, and service |  |  |  | 0
0
| Allowance for maintenance and service to the installation as described (12 months) | Item | 1 | 23760 | 23760
0
D5 | Manuals |  |  |  | 0
0
| Allowance for the provision of operating and maintenance manuals (4 sets). (Drawings in electronic Autocad format in addition to hard copies in O & M manuals) | Sets | 4 |  | 0
0
D6 | Drawings |  |  |  | 0
0
| Allowance for working drawings (Autocad) | Item | 1 | 19800 | 19800
0
| Allowance for as built drawings (Autocad) | Item | 1 | 19800 | 19800
0
D7 | Electrical Certificate of Compliance | Item | 1 | 4950 | 4950
0
D8 | Delivery, hoisting, rigging, Scaffolding | Item | 1 | 24750 | 24750
0
D9 | Compliance with the OHS Act | Item | 1 | 49500 | 49500
0
D9 | Allow an amount for the Site Establishment | No | 1 | 24750 | 24750
0
D10 | Site Store and Storeman | No | 1 | 24750 | 24750
0
D11 | Security | No | 1 | 19800 | 19800
0
D12 | Site Office | No | 1 | 9900 | 9900
0
D13 | Transport Material to Site | No | 1 | 19800 | 19800
| SCH. 000_SUB-TOTAL PAGE 4 : CARRIED FORWARD TO SCHEDULE 000 SUMMARY PAGE |  |  |  | 1122660
SCHEDULE 000 SUMMARY PAGE : PREAMBLES TO BILLS OF QUANTITIES
1 | Sub-Total Page 1
2 | Sub-Total Page 2
3 | Sub-Total Page 3
4 | Sub-Total Page 4 |  |  |  | 1122660
| TOTAL - SCHEDULE 000 : PREAMBLES TO BILLS OF QUANTITIES |  |  |  | 1122660 | 20001.96 | 20001.96 | 60000 | 20000 | 35000 | 25000 | 20000 | 0 | 0 | 200003.92

## Sched No. 600
[10 empty] | CLAIM 1 AUG |  | CLAIM 2 SEPT |  | CLAIM 3 OCT |  | CLAIM DECEMBER |  | April - Claim 7 |  | MAY - CLAIM 8 |  | JUNE CLAIM 9
ELECTRICAL INSTALLATION
Schedule No. 600 : Site Reticulation
|  |  |  | Item | Description | Unit | Qty | Rate | Amount | Current Qty | Current Claim Amount | Present Qty | Current Claim Amount | Present Qty | Current Claim Amount | Present Qty | Current Claim | Current Claim Qauntity | Current Claim Amount | Current Claim Quantity | Current Claim Amount | Current Claim Qty | Current Quantity | Current Claim Amount
|  |  |  | 1 | MV Switchgear
184500 | 5% | 6500 | 5% | 1.1 | Supply, install and commission in the Transformer Room 500kVA 11,000/400V Transformer unit with cable end boxes on both MV and LV terminals | Item | 1 | 198544.5 | 198544.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
1800 | 5% |  |  | 1.2 | Earthing of Transformer | Item | 1 | 3168 | 3168 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
16100 | 5% | 2500 | 5% | 1.3 | Metering Unit to Local Municipality or Eskom specifications | Item | 1 | 19334.7 | 19334.7 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
1200 | 5% | 350 | 5% | 1.4 | Earthing of Metering Unit | Item | 1 | 3168 | 3168 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
35000 | 5% |  |  | 1.5 | Programming of Metering Unit | Item | 1 | 36382.5 | 36382.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 2 | MV Cables - Supply and Install 11kV XLPE Cables |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
236 | 5% | 15 | 5% | 2.1 | 25mm² 3-Core 6.35/11kV cable in trench, sleeves or as required | m | 200 | 250 | 50000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 3000 | 5% | 2.2 | Outdoor termination of 25mm² 3-core XLPE cable | No. | 1 | 5017.32 | 5017.32 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 3000 | 5% | 2.3 | Indoor termination of 25mm² 3-core XLPE cable | No. | 1 | 4550 | 4550 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 3 | Standby Generator |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
1290000 | 5% | 25000 | 5% | 3.1 | Supply, install and commission in the Generator Room a 600kVA Prime Rated Indoor Type Generator unit complete with an Automatic Change-Over Panel and 1000L Diesel Tank | No. | 1 | 1366942.5 | 1366942.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
65000 | 5% | 10000 | 5% | 3.2 | Supply and install sound attenuators | Item | 1 | 77962.5 | 77962.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 3.3 | Supply first fill for diesel - 1000L | Litre | 1000 | 13.51 | 13510 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
1800 | 5% | 350 | 5% | 3.4 | Earthing of generator | Item | 1 | 2234.41 | 2234.41 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 4 | Low-Voltage (LV) Cables - supply and install 600/1000V PVC/PVC/SWA/PVC copper cable laid in trenches or fixed to cable trays (cable trays measured elsewhere) |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
892 | 5% | 15 | 5% | 4.1 | 185mm² 4-core cable | m | 2500 | 1420 | 3550000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
482 | 5% | 15 | 5% | 4.2 | 95mm² 4-core cable | m | 1500 | 610 | 915000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
355 | 5% | 15 | 5% | 4.3 | 70mm² 4-core cable | m | 1500 | 410 | 615000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
195 | 5% | 10 | 5% | 4.4 | 35mm² 4-core cable | m | 600 | 385 | 231000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
141 | 5% | 7 | 5% | 4.5 | 25mm² 4-core cable | m | 500 | 290 | 145000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | 16mm² |  |  | 169.4 | 0 | [9 empty] | 0 |  | 0 |  |  | 0
28 | 5% | 5 | 5% | 4.6 | 6mm² 2-core cable | m | 800 | 31.15 | 24920 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
23 | 5% | 5 | 5% | 4.7 | 4mm² 2-core cable | m | 800 | 20.15 | 16120 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 5 | Cable Terminations - supply and install cable terminations for 600/1000V PVC/PVC/SWA/PVC copper cables |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
333.86 | 5% | 550 | 5% | 5.1 | 185mm² 4-core cable | No. | 20 | 1089 | 21780 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
183.1 | 5% | 390 | 5% | 5.2 | 95mm² 4-core cable | No. | 16 | 970.2 | 15523.2 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
183.1 | 5% | 350 | 5% | 5.3 | 70mm² 4-core cable | No. | 12 | 559.755 | 6717.06 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
114.39 | 5% | 280 | 5% | 5.4 | 35mm² 4-core cable | No. | 10 | 311 | 3110 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
60.31 | 5% | 280 | 5% | 5.5 | 25mm² 4-core cable | No. | 10 | 301 | 3010 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
39.82 | 5% | 185 | 5% | 5.6 | 6mm² 2-core cable | No. | 20 | 260 | 5200 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
26.2 | 5% | 185 | 5% | 5.7 | 4mm² 2-core cable | No. | 20 | 210 | 4200 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 6 | Earthing - bare copper earth conductor installed and strapped to cable (cable measured elsewhere) and building earthing |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
79 | 5% | 10 | 5% | 6.1 | 70mm² BCEW | m | 950 | 67 | 63650 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
53 | 5% | 10 | 5% | 6.2 | 50mm² BCEW | m | 650 | 48.1 | 31265 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
30 | 5% | 5 | 5% | 6.3 | 25mm² BCEW | m | 500 | 29.55 | 14775 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
18 | 5% | 5 | 5% | 6.4 | 16mm² BCEW | m | 450 | 23.15 | 10417.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | 10mm |  |  | 24 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | SCH. 600_SUB-TOTAL PAGE 1 : CARRIED FORWARD TO SCHEDULE 600 SUMMARY PAGE |  |  |  | 7457502.19 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 7 | Earth Conductor Termination - termination for bare insulated copper conductors including lugs and connections | [5 empty] | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
16 | 5% | 25 | 5% | 7.1 | 70mm² BCEW | No. | 16 | 41.02 | 656.32 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
10 | 5% | 25 | 5% | 7.2 | 50mm² BCEW | No. | 14 | 37.41 | 523.74 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
6 | 5% | 25 | 5% | 7.3 | 25mm² BCEW | No. | 10 | 31.15 | 311.5 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
4 | 5% | 25 | 5% | 7.4 | 16mm² BCEW | No. | 10 | 29.2 | 292 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 8 | Sleeves - Sleeve piping including short lengths and jointing, laid in trench (trench filling measured elsewhere) |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
15 | 5% | 10 | 5% | 8.1 | 32mm diameter sleeve | m | 500 | 22 | 11000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
18 | 5% | 10 | 5% | 8.2 | 50mm diameter sleeve | m | 1500 | 22 | 33000 |  | 0 |  | 0 |  | 0 |  |  | 800 | 17600 | 750 | 16500 |  |  | 0
32 | 5% | 10 | 5% | 8.3 | 110mm diameter sleeve | m | 1800 | 25 | 45000 |  | 0 |  | 0 | 120 | 3000 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 9 | Manholes with Covers |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
6500 | 5% |  |  | 9.1 | 600mm x 600mm x 800mm (deep) manholes | No. | 40 | 2940.3 | 117612 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 5500 | 5% | 9.2 | Medium duty covers for 600mm x 600mm manholes | No. | 40 | 1568.46 | 62738.4 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 10 | Excavation of cable and sleeve pipe trenches including bedding, covering, backfilling and compaction |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 150 | 5% | 10.1 | Pickable Soil | m³ | 550 | 120 | 66000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 195 | 5% | 10.2 | Soft Rock | m³ | 500 | 250 | 125000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 550 | 5% | 10.3 | Hard Rock | m³ | 400 | 500 | 200000 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 750 | 5% | 10.4 | Extra-over for cable sleeve pipe trenches under roads, buildings, parking areas and paved areas (refer to specifications for compaction and tests | m³ | 90 | 780 | 70200 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 11 | Sundries |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
3 | 5% | 1 | 5% | 11.1 | Cable warning tape placed 300mm above cables in excavations | m | 4500 | 1.8 | 8100 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
750 | 5% |  |  | 11.2 | Concrete Plinths for Distribution Kiosks | No. | 3 | 3489 | 10467 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
79 | 5% | 10 | 5% | 11.3 | Concrete Cable Markers | No. | 10 | 152 | 1520 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 11.4 | Supply and install the following signage on the outside of the Generator Building (Block W): |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 250 | 5% | 11.4.1 | "TRANSFORMER ROOM" in black letters of size 200mm and on white background | No. | 1 | 259.87 | 259.87 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 250 | 5% | 11.4.2 | "GENERATOR ROOM" in black letters of size 200mm and on white background | No. | 1 | 259.87 | 259.87 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 250 | 5% | 11.4.3 | "UNAUTHORISED ENTRANCE PROHIBITED" | No. | 4 | 259.87 | 1039.48 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 250 | 5% | 11.4.4 | "DANGER HIGH VOLTAGE" | No. | 4 | 259.87 | 1039.48 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 11.5 | Supply and install the following signage inside the Generator/Transformer Building Rooms: |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 11.5.1 | Combination board written the following: | No. | 3 | 495 | 1485 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | UNAUTHORISED ENTRANCE PROHIBITED |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  | 500 | 5% |  | UNAUTHORISED HANDLING OF EQUIPMENT PROHIBITED |  |  | 525 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | PROCEDURES INCASE OF FIRE |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | FIRST AID INCASE OF BURNS |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | SCH. 600_SUB-TOTAL PAGE 2 : CARRIED FORWARD TO SCHEDULE 600 SUMMARY PAGE |  |  |  | 756504.66 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 12 | Distribution Boards - Supply and install distribution boards complete with sheet metal tray, frames, sub-frames, bus-bars, provision for 30% future circuit breakers and legend card as per line diagram |  |  | Material Incl |  |  | #VALUE! |  | #VALUE! |  | #VALUE! |  |  |  | #VALUE! |  | #VALUE! |  |  | #VALUE!
63499 | 5% | 5000 | 5% | 12.1 | Main Distribution Board - (See Drw: IGS/1338/DWG/00/600-50/00) | No. | 1 | 200175.12 | 200175.12 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
24303.83 | 5% | 3500 | 5% | 12.2 | Distribution Kiosk 1 - (See Drw:_ IGS/1338/DWG/00/600-60/00) | No. | 1 | 55913.34 | 55913.34 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
25292.63 | 5% | 3500 | 5% | 12.3 | Distribution Kiosk 2 - (See Drw:_ IGS/1338/DWG/00/600-70/00) | No. | 1 | 29929.94 | 29929.94 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 12.4 | Distribution Kiosk 3 - (See Drw:_ IGS/1338/DWG/00/600-80/00) | No. | 1 | 29929.94 | 29929.94 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | 13 | Luminaries - Supply and install luminaries or equipment complete with lamps, connections, etc as described in the Lighting Schedule |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0
4250 | 5% | 250 | 5% | 13.1 | Type A1 - outdoor pole light complete with 1x 70W metal halide lamp to be mounted on a black stepped 4.5m pole; fitting to be complete with a 5A circuit breaker, gland plate and access door; mounting height of light to be 3.5m. Fitting shall be SABS approved and shall be similar or equal to Radiant LS901 | No. | 80 | 4455 | 356400 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  |  | 0
3250 | 5% | 450 | 5% | 13.2 | 4.5m long black stepped pole for Type A1 lights | No. | 80 | 3454 | 276320 | 70 | 241780 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 |  |  | 0
285 | 5% | 150 | 5% | 13.3 | National 16A photocell unit with bracket | No. | 4 | 421 | 1684 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 15004440 |  |  | 0
|  |  |  | 14 | Surfix Cables |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 0 |  |  | 0
18 | 5% | 2 | 5% | 14.1 | 2,5mm² 2-core surfix cable | m | 600 | 10.66 | 6396 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 379922.4 |  |  | 0
28 | 5% | 2 | 5% | 14.2 | 4mm² 2-core surfix cable | m | 1500 | 16.01 | 24015 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 570596.4 |  |  | 0
23 | 5% | 2 | 5% | 14.3 | 6mm² 2-core surfix cable | m | 1500 | 21.54 | 32310 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 767685.6 |  |  | 0
|  |  |  | 15 | Supply and install galvanised draw-wire in all conduits and sleeve pipes |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 0 |  |  | 0
2 | 5% | 0.5 | 5% | 15.1 | 2mm diameter steel draw wire | m | 1500 | 1.5 | 2250 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 53460 |  |  | 0
|  |  |  | 16 | Other |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 0 |  |  | 0
240 | 5% | 10 | 5% | 16.1 | Key padlocks for all the distribution kiosks, switchgear, gates, doors, etc | No. | 10 | 250 | 2500 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 8910000 |  |  | 0
|  | 50000 | 5% | 16.2 | Allow for temporary power connection (25kVA) for the construction period | Item | 1 | 13860 | 13860 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 493970400 |  |  | 0
|  | 15000 | 5% | 16.3 | Testing and commissioning of complete installation | Item | 1 | 6930 | 6930 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | 35640 | 246985200 |  |  | 0
[15 empty] | 0 |  |  |  | 0 | 35640 | 0 |  |  | 0
[15 empty] | 0 |  |  |  | 0 | 35640 | 0 |  |  | 0
[15 empty] | 0 |  |  |  | 0 | 35640 | 0 |  |  | 0
[15 empty] | 0 |  |  |  | 0 | 35640 | 0 |  |  | 0
[15 empty] | 0 |  |  |  | 0 | 35640 | 0 |  |  | 0
[15 empty] | 0 |  |  |  | 0 |  | 0 |  |  | 0
|  |  |  | Repairs | Joints kits for armoured cable | No |  | 80 | [5 empty] | 4 | 320 |  |  |  | 0 |  | 0 |  |  | 0
[15 empty] | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | 1.6mm diameter steel draw wire (sleeves) | m |  | #REF! | [6 empty] | #REF! |  |  |  | #REF! | 750 | #REF! |  |  | #REF!
[15 empty] | 0 |  |  |  | 0 |  | 0 |  |  | 0
[5 empty] | 6mm x 4 core armoured cable | m |  | 90 | [6 empty] | 0 |  |  |  | 0 |  | 0 |  | 1500 | 135000
[19 empty] | 0 |  | 0 |  |  | 0
[5 empty] | Labour Rate for the installation of main cable | m |  | 45 | [10 empty] | 0 |  | 0 |  |  | 0
0
[5 empty] | CBT FD4 Pedestal plugs | No |  | 226.2 | [15 empty] | 0
0
0
[5 empty] | External Lights Labour |  | 87 | 70 | [15 empty] | 0
0
[5 empty] | Internal Lights Labour |  | 523 | 70 | [15 empty] | 0
0
0
[5 empty] | SCH. 600_SUB-TOTAL PAGE 3 : CARRIED FORWARD TO SCHEDULE 600 SUMMARY PAGE |  |  |  | 1038613.34 | [14 empty] | 0
|  |  |  | SCHEDULE 600 SUMMARY PAGE : SITE RETICULATION | [19 empty] | 0
|  |  |  | 1 | Sub-Total Page 1 |  |  |  | 7457502.19 | [14 empty] | 0
0
|  |  |  | 2 | Sub-Total Page 2 |  |  |  | 756504.66 | [14 empty] | 0
0
|  |  |  | 3 | Sub-Total Page 3 |  |  |  | 1038613.34 | [14 empty] | 0
0
[5 empty] | SCHEDULE 600 TOTAL : SITE RETICULATION |  |  |  | 9252620.19 |  | #VALUE! |  | #VALUE! |  | #VALUE! |  |  |  | #VALUE! |  | #REF! |  |  | #VALUE!